## Read_Me
Item | Notes
Status | Synthetic portfolio. No actual client, vendor award or UAT sign-off.
Currency/unit | INR; cartons; all prices exclude tax.
Formulas | Open in Excel to calculate. Formula cells are blue. Values are illustrative.
UAT | Not run. Record actual results and evidence after execution.
Prototype | Open Order_Workflow_Prototype.html locally. It covers only one-line order checks, not inventory posting or access control.

## Requirements
ID | Capability | Owner | Acceptance
REQ01 | Order capture | Distributor | Create an order with active SKUs and positive integer carton quantities; inactive products cannot be submitted.
REQ02 | Pricing and schemes | Sales operations | Use effective carton price; apply 5% discount when an order line has at least 10 cartons. No stacked discounts.
REQ03 | Credit control | Finance | Hold an order when outstanding exposure plus net order value exceeds the limit; finance approval is required to release it.
REQ04 | Inventory reservation | Warehouse | Reserve stock only after credit clearance; available stock equals on-hand minus reserved. Reject insufficient stock; no partial fulfilment in pilot.
REQ05 | Delivery | Warehouse | Dispatch reduces on-hand and releases the same reservation; a second dispatch request must not change stock.
REQ06 | Returns | Warehouse | Return quantity cannot exceed delivered less previously returned; saleable approved returns increase stock; damaged returns are quarantined.
REQ07 | Access control | Administrator | Distributor sees only its own orders. Finance releases credit holds; warehouse dispatches. Record actor, time and before/after status.
REQ08 | Migration | Data steward | Reject duplicate keys and missing references; reconcile record counts, opening stock and outstanding balances before import approval.
REQ09 | Reporting | Sales manager | Report order net value, fulfilled cartons divided by ordered cartons, held orders, and available stock by SKU. Exclude cancelled orders.
REQ10 | Integration | IT | ERP remains invoice/accounting source. Use unique order ID and retry-safe imports; put failed records into an exception queue.

## Products
SKU | Name | Price_per_carton | On_hand | Reserved | Status
SKU01 | Spiced Snack 12-pack | 1000 | 30 | 5 | Active
SKU02 | Baked Crackers 24-pack | 800 | 20 | 0 | Active
SKU03 | Fruit Bar 20-pack | 1200 | 10 | 2 | Active
SKU04 | Old Snack Pack | 700 | 15 | 0 | Inactive

## Distributors
ID | Name | Credit_limit | Outstanding
D001 | Chennai Distributor | 50000 | 42000
D002 | Bengaluru Distributor | 100000 | 20000
D003 | Hyderabad Distributor | 75000 | 70000

## Order_Model
Order_ID | Distributor | SKU | Cartons | Price | Gross | Discount_rate | Net | Outstanding | Credit_limit | Available_stock | Credit_result | Stock_result | Decision
O001 | D001 | SKU01 | 10 | 1000 |  |  |  | 42000 | 50000 | 25

## Migration
Entity | Source_field | Target_field | Rule | Error_action
Product | item_code | sku_id | Unique, nonblank | Reject duplicate/missing
Product | rate_carton | price | Positive decimal in INR | Reject invalid
Distributor | account_code | distributor_id | Unique, nonblank | Reject duplicate/missing
Distributor | unpaid_amount | outstanding | Nonnegative decimal; reconcile source sum | Reject invalid; block unmatched totals
Inventory | item_code | sku_id | Must exist in product master | Reject orphan
Inventory | stock_cartons | on_hand | Nonnegative integer; reconcile sum | Reject invalid
Inventory | reserved_cartons | reserved | 0 <= reserved <= on_hand | Reject excess
Order | account_code | distributor_id | Must exist in distributor master | Reject orphan
Order | order_no | order_id | Unique idempotency key | Reject duplicate
Order | qty | cartons | Positive integer | Reject invalid

## Vendor_Evaluation
Criterion | Weight | Vendor_A | Vendor_B | Vendor_C
Functional fit | 0.35 | 4 | 3 | 5
Integration | 0.2 | 4 | 3 | 4
Security | 0.2 | 4 | 4 | 4
Implementation/support | 0.15 | 4 | 3 | 3
Commercial clarity | 0.1 | 4 | 4 | 3
Weighted /100
Mandatory gates | Mock only | Pass assumed | Pass assumed | Pass assumed

## RFQ_Costs
Mock_vendor | Users | Monthly_per_user | Config | Migration | Integration | Training | Annual_support | 3_year_TCO
A | 20 | 1500 | 150000 | 75000 | 100000 | 30000 | 60000
B | 20 | 1200 | 100000 | 60000 | 150000 | 25000 | 80000
C | 20 | 2000 | 180000 | 100000 | 120000 | 40000 | 50000

## UAT
Test_ID | Requirement | Input_steps | Expected | Status | Actual | Evidence | Tester
T01 | REQ01 | Active SKU01, D002, 1 carton | Order passes basic checks | Not run
T02 | REQ01 | SKU04 inactive | Reject inactive SKU | Not run
T03 | REQ01 | 0, -1, 1.5 cartons | Reject each invalid quantity | Not run
T04 | REQ02 | SKU01, 9 cartons | Net 9000; no discount | Not run
T05 | REQ02 | SKU01, 10 cartons | Net 9500; 5% discount | Not run
T06 | REQ03 | D001, SKU01, 10 cartons | Exposure 51500; HOLD; no reservation | Not run
T07 | REQ03 | Exposure exactly credit limit | CLEAR; equality is allowed | Not run
T08 | REQ04 | SKU03, 9 cartons; available 8 | Reject insufficient stock | Not run
T09 | REQ04 | SKU03, 8 cartons; available 8; D002 | Pass stock boundary | Not run
T10 | REQ05 | Dispatch reserved 10 twice | First updates stock; second rejected/no change | Not run
T11 | REQ06 | Deliver 10, previously return 2, new return 9 | Reject over-return | Not run
T12 | REQ06 | Saleable 2 / damaged 2 | Saleable adds 2; damaged quarantine only | Not run
T13 | REQ07 | D001 requests D002 order | Deny access | Not run
T14 | REQ07 | Distributor requests credit release | Deny; finance approval only | Not run
T15 | REQ08 | Duplicate SKU/orphan order | Reject rows; show reasons | Not run
T16 | REQ08 | Opening stock/balance sum mismatch | Block import sign-off | Not run
T17 | REQ09 | Orders 10+10; delivered 10+5 | Fill rate 75% excluding cancelled orders | Not run
T18 | REQ10 | Same ERP event twice | One posting; return original acknowledgement | Not run

## RTM
Requirement | Design | Tests | Evidence_status
REQ01 | Order capture | T01, T02, T03 | Awaiting execution
REQ02 | Pricing and schemes | T04, T05 | Awaiting execution
REQ03 | Credit control | T06, T07 | Awaiting execution
REQ04 | Inventory reservation | T08, T09 | Awaiting execution
REQ05 | Delivery | T10 | Awaiting execution
REQ06 | Returns | T11, T12 | Awaiting execution
REQ07 | Access control | T13, T14 | Awaiting execution
REQ08 | Migration | T15, T16 | Awaiting execution
REQ09 | Reporting | T17 | Awaiting execution
REQ10 | Integration | T18 | Awaiting execution

## Defects
ID | Test | Severity | Scenario | Expected | Actual | Status
EXAMPLE_ONLY | T05 | High | Hypothetical threshold defect | 5% at 10 cartons | Hypothetical 0% at 10 | Illustrative, not observed

## Feedback
Session_date | Reviewer_role | Task | Observation | Change | Owner | Status
| Distributor | Submit order and explain hold |  |  |  | Pending role-play
| Finance | Explain credit review and release |  |  |  | Pending role-play

## Go_Live
Check | Owner | Evidence | Status
Opening balance reconciled | Finance |  | Pending
Master/stock counts reconciled | Data steward |  | Pending
Access isolation tested | IT |  | Pending
Critical UAT passed | Business owners |  | Pending
Training completed | BA |  | Pending
Rollback export verified | IT |  | Pending
Sponsor approval obtained | Sponsor |  | Pending